## Sheet1
CVOW - overview of local subcontractor needs DEMIAN
ID | Potential local subcontractor scope | Company | Equipment needs description | Personnel needs description | Land/Office Space Needed | Quayside or land-based service needed | Start - end of works
1 | AFFF / Fire suppression systems equipment, Fire Safety Equipment | DEME |  |  |  | Land-based service | Q2 2024 - Q2 2026
2 | Bus Service | DEME |  |  |  | Land-based service | Q2 2024 - Q2 2026
3 | Cable Float buoy supplier | DEME |  |  |  | Land-based service | TBD
4 | Cable land fall pull in assistance | Prysmian | Work boats Divers Excavators 50t Winch Jack Up Barge Diesel generator | Experienced on Cable landing operation or at least similar activities. Experienced civil subcontractor. | Landfall site | Quayside & offshore service | TBD
5 | Cable Termination & Testing Services | DEME | Cable Testing Equipment | Experienced Cable Testing Personnel |  | Quayside & offshore service | Q2 2025 - Q2 2026
6 | Cable Tracking (experienced electrical subcontractor) | Prysmian | Diesel Generator | Experience electrical subcontractor | Landfall site | Quayside & offshore service | Prysmian to add
7 | Catering vessels | DEME, Prysmian | Catering vessel | Marine crew | Quayside/marine port |  | Q2 2024 - Q2 2026
8 | Consultancy services | DEME |  | Consultants in various fields (engineering, permitting, legal, etc.) |  | Land-based service | Q2 2024 - Q2 2026
9 | Crew Transfer Vessel | DEME, Prysmian | Crew Transfer Vessels of adequate size and quality | Marine Crew | Quayside/marine port | Quayside & Offshore service | Q2 2024 - Q2 2026
10 | Clothing / Workwear | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
11 | Container (DNV)(ABS) | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
12 | Cordage / Mooring lines | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
13 | Courier services | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
14 | Customs agent | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
15 | Cranes - all tonnages | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
16 | Deck (ship) equipment; windlass, seals, deck winches, measuring equipment, secondary steel framing, signage, etc. | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
17 | Electrical equipment (incl. Pneumatic) | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
18 | Engine (ship) supply - domestic & metric | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
19 | Fuel Suppliers | DEME, Prysmian | Bunkering spread and trucks | Truck drivers |  | Quayside service | Q2 2024 - Q2 2026
20 | Frog Offshore Personnel Transfer pods | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
21 | Full 3PL company | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
22 | Gas supplier (Argon, etc.) | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
23 | Grout material | DEME | Grout | Grout supplier |  | Quayside & Offshore service | Q2 2024 - Q2 2026
24 | Grout Spread | DEME | Grouting spread | Experienced Grouting Crew & Marine Crew |  | Offshore service | Q2 2024 - Q2 2026
25 | GWO Training | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
26 | Harbour Tug Boats | DEME | Tug boats | Marine Crew | Quayside/marine port | Quayside service | Q2 2024 - Q2 2026
27 | Hardware stores | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
28 | Hazmat removal | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
29 | Heavy equip rental | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
30 | Heli-Transfer gear; carabiners, shackles, harnesses, etc. | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
31 | Helicopter services | DEME | Helicopters for offshore crew transfers | Helicopter pilots & supporting personnel | Heliport | Land-based & Offshore service | Q2 2024 - Q2 2026
32 | Hotels for corp rates, etc. | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
33 | Housing - project: - utilities (water, sewer, elec. (if not included in lease) - cleaning services - furniture lease or purchase | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
34 | HPUs | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
35 | IT setup / IT Support service | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
36 | Jack up Vessel (optional) | DEME | Jack-up Vessel | Marine Crew |  | Quayside & offshore service | Q2 2024 - Q2 2026
37 | Licensed shoreside electrician | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
38 | Light equip rental ( forks, pallet jacks, man lifts, etc.) | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
39 | Lumber supplier / yard with small design/ building capabilities | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
40 | Marine electrician | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
41 | Marine Fender (heavy) | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
42 | Marine Fuel supplier (aux gen diesel, etc) | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
43 | Marine generator rental | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
44 | Marine hydraulics | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
45 | Marine lubricants | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
46 | Marine paint | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
47 | NDT / MPI | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
48 | Offices: - utilities (water, sewer, elec. (if not included in lease) - cleaning services - supply services (cantina, desk materials) - furniture lease or purchase - WIFI | DEME, Prysmian | Offices & supporting services | Office management personnel (cleaning services, etc.) | Office space | Land-based service | Q2 2024 - Q2 2026
49 | Oil Spill response services | DEME, Prysmian | Oil spill response vessel | Experienced Marine Crew |  | Offshore service | Q2 2024 - Q2 2026
50 | Passive Acoustic Monitoring (PAM) | DEME | PAM equipment | Experienced PAM crew |  | Quayside & Offshore service | Q2 2024 - Q2 2026
51 | Painting Equipment | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
52 | PFD supplier (personal floatation device) | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
53 | Personal Protection Equipment (PPE) | DEME | PPE | PPE supplier |  | Land-based service | Q2 2024 - Q2 2026
54 | Protected Species Observers (PSO) | DEME | PSO monitoring equipment | Experienced Protected Species Observers |  | Quayside & Offshore service | Q2 2024 - Q2 2026
55 | Provisioner (ship) | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
56 | Real estate (residential full service agency) | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
57 | Rental cars | DEME, Prysmian | Taxi's, rental cars, etc. | Taxi drivers, etc. |  | Land-based service | Q2 2024 - Q2 2026
58 | Rigging (light and heavy duty) | DEME | Various rigging | Rigging supplier |  | Land-based service | Q2 2024 - Q2 2026
59 | ROVs | DEME, Prysmian | ROV equipment | Experienced ROV operators | Quayside/marine port | Quayside & Offshore service | Q2 2024 - Q2 2026
60 | Safety supplier (SOLAS/USCG) | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
61 | Scaffolding services | DEME | Scaffolds | Certified scaffolders |  | Quayside & offshore service | Q2 2024 - Q2 2026
62 | Support vessels (type fishing vessels for use by protected species observers, survey vessels, etc.) | DEME | Scout vessel | Marine Crew | Quayside/marine port | Quayside & Offshore service | Q2 2024 - Q2 2026
63 | Security fence supplier | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
64 | Shipping & Logistics Services | DEME, Prysmian |  | Shipping agents | Office space | Quayside & offshore service | Q2 2024 - Q2 2026
65 | Small handling tools | DEME | Various tools | Tool supplier |  | Land-based & quayside service | Q2 2024 - Q2 2026
66 | Staffing / Ex mil recruiting | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
67 | Steel fabricator / supplier - plate - secondary - rolled - pipe | DEME, Prysmian | Seafastening structures | Experienced steel construction company |  | Land-based service | Q2 2024 - Q2 2026
68 | Storage // Warehousing | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
69 | Project personnel (operational staff, HSE staff, etc.) | DEME |  | Experienced operational staff, HSE staff, etc. |  | Land-based & Offshore service | Q2 2024 - Q2 2026
70 | Safety advisors | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
71 | Survey works | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
72 | TJB construction and jointing support | Prysmian | Excavators, Crane, Diesel generator, Welfare facilities | Experienced civil subcontractor | Landfall site | Quayside & offshore service | Q2 2024 - Q2 2026
73 | Towing Tug | Prysmian |  | Experienced Offshore contractor |  | Quayside & offshore service | Q2 2024 - Q2 2026
74 | Taxi Service | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
75 | Temp services rental (aux power, aux air, aux H20) | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
76 | Tool (hand) supplier ( i.e. Furgeson) (domestic & metric) | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
77 | Trash removal service | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
78 | UHF Radios | DEME, Prysmian |  |  |  |  | Q2 2024 - Q2 2026
79 | Vessel Lubricants Suppliers | DEME, Prysmian | Lubricants supply spread | Lubricant supplier |  | Quayside service | Q2 2024 - Q2 2026
80 | Vessel repair & general repair services (steelworks, welders, hydraulics,…) | DEME, Prysmian | Welding equipment, steel, hydraulic components, etc. | Welders, steel supplier, hydraulic component supplier, technicians | Quayside/marine port | Land-based & quayside service | Q2 2024 - Q2 2026
81 | Weather forecast services | DEME | Weather monitoring equipment | Weather forecasting organisation |  | Land-based & Offshore service | Q2 2024 - Q2 2026
82 | Winches (all sizes) | [5 empty] | Q2 2024 - Q2 2026
83 | Welding and NDT services | DEME | Welding and NDT Equipment | Welding and NDT personnel | Quayside/marine port | Quayside service | Q2 2024 - Q2 2026
84 | Workshop Containers | DEME | Containers | Container supplier |  | Quayside service | Q2 2024 - Q2 2026