## Sheet1
CVOW - overview of local subcontractor needs Balicore | [7 empty] | Legend: | Contracts Ongoing
Contacts Required Later
ID | Potential local subcontractor scope | Equipment / Material Needs Description | Service Needs Description | Personnel Hiring Needs Description | Start of Services | Duration of Services | Status/priority |  | Contacts Requested
Urgent Need for Contacts
1 | *Concrete | N/A | See column "C" | N/A | Q2-2024 | Q3-2024
2 | Steel, Misc Metals, & Stairs | N/A | See column "C" | N/A | Q3-2024 | Q1-2025
3 | Precast Stairs | N/A | See column "C" | N/A | Q3-2024 | Q3-2024
4 | *Framing/Sheathing/Insulation/Drywall/Ceilings/Blocking | N/A | See column "C" | N/A | Q3-2024 | Q4-2024
5 | *Mass Timber | N/A | See column "C" | N/A | Q4-2024 | Q1-2025
6 | *PEMB | N/A | See column "C" | N/A | Q3-2024 | Q1-2025
7 | *Building Skin | N/A | See column "C" | N/A | Q3-2025 | Q3-2025
8 | *Roof | N/A | See column "C" | N/A | Q4-2024 | Q4-2024
9 | Sealant | N/A | See column "C" | N/A | Q4-2024 | Q4-2025
10 | Doors and Hardware | N/A | See column "C" | N/A | Q3-2025 | Q3-2025
11 | OH Doors | N/A | See column "C" | N/A | Q4-2024 | Q4-2024
12 | *Aluminum Storefront, Glazing and Doors | N/A | See column "C" | N/A | Q1-2025 | Q2-2025
13 | Tile, Flooring & Base | N/A | See column "C" | N/A | Q3-2025 | Q3-2025
14 | Access Floor | N/A | See column "C" | N/A | Q3-2025 | Q3-2025
15 | Paint | N/A | See column "C" | N/A | Q2-2025 | Q3-2025
16 | Misc Specialties | N/A | See column "C" | N/A | Q3-2025 | Q3-2025
17 | Flag Poles | N/A | See column "C" | N/A | Q3-2025 | Q3-2025
18 | Canopies? | N/A | See column "C" | N/A | Q4-2024 | Q4-2025
19 | Fencing | N/A | See column "C" | N/A | Q3-2025 | Q3-2025
20 | Demountable Partitions | N/A | See column "C" | N/A | Q3-2025 | Q3-2025
21 | Cabinets and Counters | N/A | See column "C" | N/A | Q3-2025 | Q3-2025
22 | *Furniture | N/A | See column "C" | N/A | Q3-2025 | Q3-2025
23 | Elevator | N/A | See column "C" | N/A | Q2-2025 | Q3-2025
24 | *Fire Protection | N/A | See column "C" | N/A | Q3-2024 | Q2-2025
25 | *Plumbing & HVAC | N/A | See column "C" | N/A | Q2-2025 | Q3-2025
26 | *Electrical, FA & Comms | N/A | See column "C" | N/A | Q3-2024 | Q3-2025
27 | *Piles | N/A | See column "C" | N/A | Q1-2024 | Q2-2024
29 | Solar Panels | N/A | See column "C" | N/A | Q3-2025 | Q3-2025
30 | Guard Booths | N/A | See column "C" | N/A | Q3-2025 | Q3-2025
31 | Security Gates | N/A | See column "C" | N/A | Q3-2025 | Q3-2025
32 | *Site Grading, Utilities, Paving, Bollards, etc | N/A | See column "C" | N/A | Q1-2024 | Q3-2025
33 | Landscaping | N/A | See column "C" | N/A | Q3-2025 | Q3-2025
34 | *Marine Work | N/A | See column "C" | N/A | Q2-2025 | Q3-2025
35 | Pier Wet Utilities | N/A | See column "C" | N/A | Q3-2025 | Q3-2025
36 | Pier Electical | N/A | See column "C" | N/A | Q2-2025 | Q2-2025
37
38
39
40
Rental Agreements, PSAs and POs
1 | Trailers | N/A | See column "C" | N/A | Q1-2024 | Q4-2025
2 | Cranes | N/A | See column "C" | N/A | Q1-2024 | Q1-2025
3 | Temporary Fencing | N/A | See column "C" | N/A | Q1-2025 | Q4-2025
5 | Equipment Rental | N/A | See column "C" | N/A | Q1-2024 | Q4-2025
6 | Scaffolding | N/A | See column "C" | N/A | Q3-2024 | Q3-2025
7 | Dumpsters | N/A | See column "C" | N/A | Q1-2024 | Q4-2025
8 | Portajohns | N/A | See column "C" | N/A | Q1-2024 | Q4-2025
9 | Temporary Carpenters and Laborers | N/A | N/A | See column "C" | Q2-2024 | Q3-2025
10
11
12
13
14
15
16
17
18
19
20